## Sheet1
Activities | Planned Start Date | Actual Start Date | End Date | Status | Description
Pre-Work
Formulate problem statement | 2020-04-15 |  | 2020-04-20 |  | Defined project scope.
Data Gathering | 2020-04-20 |  | 2020-04-25 |  | Explore different platform to identify sales data
Tool/Technology Identification | 2020-04-26 |  | 2020-04-30 |  | Python, Packages- seaborn, Matplotlib, numpy, sklearn, wordcloud, IPython.display
Data Preparation | 2020-05-01 |  | 2020-05-10
Data understading/Discovery |  |  |  |  | Data verification and Analyze significance of all data features
Data filtering/Cleaning |  |  |  |  | Analyze significance of all data features and remove unwanted features. Identifying data for creating a prototype model
Tranforming |  |  |  |  | Sanity check of the important data
Model/Algorithm Development | 2020-05-15 |  | 2020-06-15
Model Selection/Creation |  |  |  |  | Identify different models for classfication
Model Training/Validation |  |  |  |  | Split data in train and test
Model Implementation |  |  |  |  | Implement different models on training data
Model Optimization |  |  |  |  | Hyperparameter tuning different models to improve accuracy
Final Deployment | 2020-06-16 |  | 2020-06-18